## Flats
TOWER |  |  | A | ELV Flats Work Prograsse
Last Updadte : |  |  | 30/6/2026
Time : |  |  | 10
Flat Number | Tower | Floor number | Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Ground Pipe | Pipe | Wireing |  |  |  | Nots
[10 empty] | Data | intercome | Home Automations | 220v
1
101 | A | 1 | 2BHK | done | done | done | done | done | done | done | done | done | done | cabinet paint damage
102 | A | 1 | 2BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
103 | A | 1 | 1BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
104 | A | 1 | 1BHK | done | done | done | done | done | done | done | done | done | done
105 | A | 1 | 2BHK | done | done | done | done | done | done | done | done | done | done
106 | A | 1 | 1BHK | done | done | done | done | done | done | done | pending | done | done | no inter come pipe
107 | A | 1 | 2BHK | done | done | done | done | done | done | done | done | done | done
108 | A | 1 | studio | done | done | done | done | done | done | done | done | done | done
109 | A | 1 | studio | done | done | done | done | done | done | done | done | done | done
110 | A | 1 | studio | done | done | done | done | done | done | done | done | done | done
111 | A | 1 | studio | done | done | done | done | done | done | done | done | done | done
112 | A | 1 | 1BHK | done | done | done | done | done | done | done | done | done | done | need connections form main pipe to socket
113 | A | 1 | studio | done | done | done | done | done | done | done | pending | done | done
2
201 | A | 2 | 2BHK | done | done | done | done | done | done | done | done | done | done
202 | A | 2 | 2BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
203 | A | 2 | 1BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
204 | A | 2 | 1BHK | done | done | done | done | done | done | done | done | done | done
205 | A | 2 | 2BHK | done | done | done | done | done | done | done | done | done | done
206 | A | 2 | 1BHK | done | done | done | done | done | done | done | pending | done | done | no inter come pipe
207 | A | 2 | 2BHK | done | done | done | done | done | done | done | done | done | done | need connections form main pipe to socket
208 | A | 2 | studio | done | done | done | done | done | done | done | pending | done | done
209 | A | 2 | studio | done | done | done | done | done | done | done | pending | done | done
210 | A | 2 | studio | done | done | done | done | done | done | done | pending | done | done
211 | A | 2 | studio | done | done | done | done | done | done | done | pending | done | done
212 | A | 2 | 1BHK | done | done | done | done | done | done | done | pending | done | done
213 | A | 2 | 1BHK | done | done | done | done | done | done | done | pending | done | done
214 | A | 2 | studio | done | done | done | done | done | done | done | pending | done | done
3
301 | A | 3 | 2BHK | done | done | done | done | done | done | done | done | done | done | no ground pipe
302 | A | 3 | 2BHK | done | done | done | done | done | done | pending | pending | done | done | long spring cable pulling needed
303 | A | 3 | 1BHK | done | done | done | done | done | done | pending | pending | done | done | long spring cable pulling needed
304 | A | 3 | 1BHK | done | done | done | done | done | done | done | done | done | done | no ground pipe
305 | A | 3 | 2BHK | done | done | done | done | done | done | done | done | done | done | need connections form main pipe to socket
306 | A | 3 | 1BHK | done | done | done | done | done | done | pending | done | done | done | no ground pipe
307 | A | 3 | 2BHK | done | done | done | done | done | done | pending | done | done | done | no ground pipe
308 | A | 3 | studio | done | done | done | done | done | done | pending | done | done | done | no ground pipe
309 | A | 3 | studio | done | done | done | done | done | done | done | done | done | done
310 | A | 3 | studio | done | done | done | done | done | done | done | done | done | done
311 | A | 3 | studio | done | done | done | done | done | done | done | done | done | done
312 | A | 3 | 1BHK | done | done | done | done | done | done | pending | done | done | done | no ground pipe
313 | A | 3 | 1BHK | done | done | done | done | done | done | pending | done | done | done | no ground pipe
314 | A | 3 | studio | done | done | done | done | done | done | pending | done | done | done | no ground pipe
d
401 | A | 4 | 2BHK | done | done | done | done | done | done | done | done | done | done | need connections form main pipe to socket
402 | A | 4 | 2BHK | done | done | done | done | pending | done | pending | pending | done | done | no ground pipe
403 | A | 4 | 1BHK | done | done | done | done | pending | done | done | pending | done | done | no ground pipe
404 | A | 4 | 1BHK | done | done | done | done |  | done | pending | pending | done | done
405 | A | 4 | 2BHK | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
406 | A | 4 | 1BHK | done | done | done | done |  | done | done | done | done | done
407 | A | 4 | 2BHK | done | done | done | done |  | done | done | done | done | done
408 | A | 4 | studio | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
409 | A | 4 | studio | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
410 | A | 4 | studio | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
411 | A | 4 | studio | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
412 | A | 4 | 1BHK | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
413 | A | 4 | 1BHK | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
414 | A | 4 | studio | done | done | done | done |  | done | done | done | done | done | need connections form main pipe to socket
5
501 | A | 5 | 2BHK | done | done | done | done |  | done |  |  | done | done
502 | A | 5 | 2BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
503 | A | 5 | 1BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
504 | A | 5 | 1BHK | done | done | done | done |  | done |  |  | done | done
505 | A | 5 | 2BHK | done | done | done | done |  | done |  |  | done | done
506 | A | 5 | 1BHK | done | done | done | done |  | done |  |  | done | done
507 | A | 5 | 2BHK | done | done | done | done |  | done |  |  | done | done
508 | A | 5 | studio | done | done | done | done |  | done |  |  | done | done
509 | A | 5 | studio | done | done | done | done |  | done |  |  | done | done
510 | A | 5 | studio | done | done | done | done |  | done |  |  | done | done
511 | A | 5 | studio | done | done | done | done |  | done |  |  | done | done
512 | A | 5 | 1BHK | done | done | done | done |  | done |  |  | done | done
513 | A | 5 | 1BHK | done | done | done | done |  | done |  |  | done | done
514 | A | 5 | studio | done | done | done | done |  | done |  |  | done | done
6
601 | A | 6 | 2BHK | done | done | done | done |  | done |  |  | done | done
602 | A | 6 | 2BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
603 | A | 6 | 1BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
604 | A | 6 | 1BHK | done | done | done | done |  | done |  |  | done | done
605 | A | 6 | 2BHK | done | done | done | done |  | done |  |  | done | done
606 | A | 6 | 1BHK | done | done | done | done |  | done |  |  | done | done
607 | A | 6 | 2BHK | done | done | done | done |  | done |  |  | done | done
608 | A | 6 | studio | done | done | done | done |  | done |  |  | done | done
609 | A | 6 | studio | done | done | done | done |  | done |  |  | done | done
610 | A | 6 | studio | done | done | done | done |  | done |  |  | done | done
611 | A | 6 | studio | done | done | done | done |  | done |  |  | done | done
612 | A | 6 | 1BHK | done | done | done | done |  | done |  |  | done | done
613 | A | 6 | 1BHK | done | done | done | done |  | done |  |  | done | done
614 | A | 6 | studio | done | done | done | done |  | done |  |  | done | done
7
701 | A | 7 | 2BHK | done | done | done | done |  | done |  |  | done | done
702 | A | 7 | 2BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
703 | A | 7 | 1BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
704 | A | 7 | 1BHK | done | done | done | done |  | done |  |  | done | done
705 | A | 7 | 2BHK | done | done | done | done |  | done |  |  | done | done
706 | A | 7 | 1BHK | done | done | done | done |  | done |  |  | done | done
707 | A | 7 | 2BHK | done | done | done | done |  | done |  |  | done | done
708 | A | 7 | studio | done | done | done | done |  | done |  |  | done | done
709 | A | 7 | studio | done | done | done | done |  | done |  |  | done | done
710 | A | 7 | studio | done | done | done | done |  | done |  |  | done | done
711 | A | 7 | studio | done | done | done | done |  | done |  |  | done | done
712 | A | 7 | 1BHK | done | done | done | done |  | done |  |  | done | done
713 | A | 7 | 1BHK | done | done | done | done |  | done |  |  | done | done
714 | A | 7 | studio | done | done | done | done |  | done |  |  | done | done
8
801 | A | 8 | 2BHK | done |  | done
802 | A | 8 | 2BHK | done |  | done
long spring cable pulling needed
803 | A | 8 | 1BHK | done |  | done
long spring cable pulling needed
804 | A | 8 | 1BHK | done |  | done
805 | A | 8 | 2BHK | done |  | done
806 | A | 8 | 1BHK | done |  | done
807 | A | 8 | 2BHK | done |  | done
808 | A | 8 | studio | done |  | done
809 | A | 8 | studio | done |  | done
810 | A | 8 | studio | done |  | done
811 | A | 8 | studio | done |  | done
812 | A | 8 | 1BHK | done |  | done
813 | A | 8 | 1BHK | done |  | done
814 | A | 8 | studio | done |  | done
9
901 | A | 9 | 2BHK
902 | A | 9 | 2BHK
903 | A | 9 | 1BHK
904 | A | 9 | 1BHK
905 | A | 9 | 2BHK
906 | A | 9 | 1BHK
907 | A | 9 | 2BHK
908 | A | 9 | studio
909 | A | 9 | studio
910 | A | 9 | studio
911 | A | 9 | studio
912 | A | 9 | 1BHK
913 | A | 9 | 1BHK
914 | A | 9 | studio
Roof

## Floors
TOWER | A | ELV Floors Work Prograsse
Last Updadte : | 25/06/2026
Time : | 12.3
ELV system | Point | Location | Additional details | Phase | [7 empty] | Floor | Completed works | Nots
|  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
Bassment 1
CCTV | B1 CAM 1 | STAIR 2 | 120% ID VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 2 | STAIR 1 | 120% ID VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 3 | ENTRY-1 | 25% OBS VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 4 | ENTRY-2 | 120% ID VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 5 | LIFT LOBBY-1 | 25% OBS VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 6 | LIFT LOBBY-2 | 120% ID VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 7 | VIEW-1 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 8 | VIEW-2 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 9 | RAMP1 | 120% ID VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 10 | DRIVE WAY1 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 11 | DRIVE WAY2 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 12 | DRIVE WAY3 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 13 | DRIVE WAY4 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 14 | DRIVE WAY5 | 120% ID VIEW | done |  | done | done |  |  |  |  | B1
| B1 CAM 15 | RAMP2 | 10% DET VIEW | done |  | done | done |  |  |  |  | B1
Access Control | CR: Card Reader | Lift lobby 1 | [9 empty] | B1
| ML: Magnetic Lock (القفل المغناطيسي) | Lift lobby 2 | [9 empty] | B1
| DRC: Door Release/Contact (جهاز إطلاق/اتصال الباب) | Lift lobby 3 | [9 empty] | B1
| DC: Door Contact (مستشعر حالة الباب) | Lift lobby 4 | [9 empty] | B1
| JB: Junction Box (صندوق التوصيل) | Lift lobby 5 | [9 empty] | B1
| DB: Distribution Board (لوحة التوزيع) | Lift lobby 6 | [9 empty] | B1
| LC: Lock Controller (متحكم القفل) | Lift lobby 7 | [9 empty] | B1 |  |  |  | Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
| CR: Card Reader | Stiar-2 | [9 empty] | B1 |  |  |  | Fiber Optic | 214: N/A
| ML: Magnetic Lock (القفل المغناطيسي) | Stiar-3 | [9 empty] | B1
| DC: Door Contact (مستشعر حالة الباب) | Stiar-4 | [9 empty] | B1
| JB: Junction Box (صندوق التوصيل) | Stiar-5 | [9 empty] | B1
| DB: Distribution Board (لوحة التوزيع) | Stiar-6 | [9 empty] | B1 |  |  |  | Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Bassment 2
CCTV | [11 empty] | B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
Access Control | [11 empty] | B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
B2
Ground Floor
CCTV | [11 empty] | G
G
G
G
G
G
G
G
G
G
G
G
G
G
G
Access Control | [11 empty] | G
G
G
G
G
G
Gate Barrier | [11 empty] | G
G
G
G
G
G
poduim Floor
CCTV | [11 empty] | Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Access Control | [11 empty] | Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
Gate Barrier | [11 empty] | Poduim
Poduim
Poduim
Poduim
Poduim
Poduim
1 St floor
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 3 | stair1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 4 | stair2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 7 | over view1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 8 | over view2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 9 | over view3 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 10 | over view4 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 11 | over view5 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
intercom | 101 |  |  | done |  | done | done |  |  |  |  | 1
| 102 |  |  | done |  | done | pendding |  |  |  |  | 1
| 103 |  |  | done |  | done | pendding |  |  |  |  | 1
| 104 |  |  | done |  | done | [5 empty] | 1
| 105 |  |  | done |  | done | [5 empty] | 1
| 106 |  |  | done |  | done | pendding |  |  |  |  | 1
| 107 |  |  | done |  | done | [5 empty] | 1
| 108 |  |  | done |  | done | [5 empty] | 1
| 109 |  |  | done |  | done | [5 empty] | 1
| 110 |  |  | done |  | done | [5 empty] | 1
| 111 |  |  | done |  | done | [5 empty] | 1
| 112 |  |  | done |  | done | [5 empty] | 1
| 113 |  |  | done |  | done | [5 empty] | 1
Fiber Optic | 101 | [10 empty] | 1
| 102 | [10 empty] | 1
| 103 | [10 empty] | 1
| 104 | [10 empty] | 1
| 105 | [10 empty] | 1
| 106 | [10 empty] | 1
| 107 | [10 empty] | 1
| 108 | [10 empty] | 1
| 109 | [10 empty] | 1
| 110 | [10 empty] | 1
| 111 | [10 empty] | 1
| 112 | [10 empty] | 1
| 113 | [10 empty] | 1
2nd Floor
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2 |  | pendding Long spring cable pulling required
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2 |  | pendding Long spring cable pulling required
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
intercom | 201 |  |  | done |  | done | done |  |  |  |  | 2
| 202 |  |  | done |  | pendding | pendding |  |  |  |  | 2 |  | pendding Long spring cable pulling required
| 203 |  |  | done |  | pendding | pendding |  |  |  |  | 2 |  | pendding Long spring cable pulling required
| 204 |  |  | done |  | done | done |  |  |  |  | 2
| 205 |  |  | done |  | done | done |  |  |  |  | 2
| 206 |  |  | done |  | done | done |  |  |  |  | 2
| 207 |  |  | done |  | done | done |  |  |  |  | 2 |  | need pipe to backbox connections | .
| 208 |  |  | done |  | pending | pending |  |  |  |  | 2
| 209 |  |  | done |  | pending | pending |  |  |  |  | 2
| 210 |  |  | done |  | pending | pending |  |  |  |  | 2
| 211 |  |  | done |  | pending | pending |  |  |  |  | 2
| 212 |  |  | done |  | pending | pending |  |  |  |  | 2
| 213 |  |  | done |  | pending | pending |  |  |  |  | 2 |  | An external pipe extension is needed to the ELV room.
| 214 |  |  | done |  | pending | pending |  |  |  |  | 2
Fiber Optic | 201 |  |  | done | [7 empty] | 2
| 202 |  |  | done | [7 empty] | 2
| 203 |  |  | done | [7 empty] | 2
| 204 |  |  | done | [7 empty] | 2
| 205 |  |  | done | [7 empty] | 2
| 206 |  |  | done | [7 empty] | 2
| 207 |  |  | done | [7 empty] | 2
| 208 |  |  | done | [7 empty] | 2
| 209 |  |  | done | [7 empty] | 2
| 210 |  |  | done | [7 empty] | 2
| 211 |  |  | done | [7 empty] | 2
| 212 |  |  | done | [7 empty] | 2
| 213 |  |  | done | [7 empty] | 2
| 214 |  |  | done | [7 empty] | 2
3nd Floor
CCTV | 3nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 3
| 3nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
intercom | 301 |  |  | done |  | done | done |  |  |  |  | 3
| 302 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 303 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 304 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 305 |  |  | done |  | done | done |  |  |  |  | 3
| 306 |  |  | done |  | done | done |  |  |  |  | 3
| 307 |  |  | done |  | done | done |  |  |  |  | 3
| 308 |  |  | done |  | done | done |  |  |  |  | 3
| 309 |  |  | done |  | done | done |  |  |  |  | 3
| 310 |  |  | done |  | pending | pending |  |  |  |  | 3
| 311 |  |  | done |  | done | done |  |  |  |  | 3
| 312 |  |  | done |  | pending | pending |  |  |  |  | 3
| 313 |  |  | done |  | pending | pending |  |  |  |  | 3
| 314 |  |  | done |  | done | done |  |  |  |  | 3
Fiber Optic | 301 |  |  | done | [7 empty] | 3
| 302 |  |  | done | [7 empty] | 3
| 303 |  |  | done | [7 empty] | 3
| 304 |  |  | done | [7 empty] | 3
| 305 |  |  | done | [7 empty] | 3
| 306 |  |  | done | [7 empty] | 3
| 307 |  |  | done | [7 empty] | 3
| 308 |  |  | done | [7 empty] | 3
| 309 |  |  | done | [7 empty] | 3
| 310 |  |  | done | [7 empty] | 3
| 311 |  |  | done | [7 empty] | 3
| 312 |  |  | done | [7 empty] | 3
| 313 |  |  | done | [7 empty] | 3
| 314 |  |  | done | [7 empty] | 3
4th Floor
CCTV | 4nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 4
| 4nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | pending |  |  |  |  | 4 |  | long spring needed
| 4nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
Inter Come | 401 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 402 |  |  | done |  | pending | pending |  |  |  |  | 4 |  | need long cable pulling spring
| 403 |  |  | done |  | pending | pending |  |  |  |  | 4 |  | need long cable pulling spring
| 404 |  |  | done |  | done | done |  |  |  |  | 4
| 405 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 406 |  |  | done |  | done | done |  |  |  |  | 4
| 407 |  |  | done |  | done | done |  |  |  |  | 4
| 408 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 409 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 410 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 411 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 412 |  |  | done |  | pending | pending |  |  |  |  | 4 |  | no pipe
| 413 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
| 414 |  |  | done |  | done | done |  |  |  |  | 4 |  | need pipe to backbox connections
Fiber Optic | 401 |  |  | done | [7 empty] | 4
| 402 |  |  | done | [7 empty] | 4
| 403 |  |  | done | [7 empty] | 4
| 404 |  |  | done | [7 empty] | 4
| 405 |  |  | done | [7 empty] | 4
| 406 |  |  | done | [7 empty] | 4
| 407 |  |  | done | [7 empty] | 4
| 408 |  |  | done | [7 empty] | 4
| 409 |  |  | done | [7 empty] | 4
| 410 |  |  | done | [7 empty] | 4
| 411 |  |  | done | [7 empty] | 4
| 412 |  |  | done | [7 empty] | 4
| 413 |  |  | done | [7 empty] | 4
| 414 |  |  | done | [7 empty] | 4