## STATICS
Total Number of First fix copleted flat | 56 | Towe A | Num of ONU | Completed | Available | Towe B | Num of ONU | Completed | Available
|  | 1 | 13 | 13 |  | 1 | 7 | 7
|  | 2 | 14 | 14 |  | 2 | 8 | 8
|  | 3 | 14 | 14 |  | 3 | 8 | 0 | 8
|  | 4 | 14 | 14 |  | 4 | 8 | 0
|  | 5 | 14 | 14 | 4 | 5 | 8 | 0
|  | 6 | 14 | 14 | 14 | 6 | 8 | 0
|  | 7 | 14 | 0 | 14 | 7 | 8 | 0
|  | 8 | 14 | 0 | 14 | 8 | 7 | 0
|  | 9 | 14 | 0 | 14 | 9 | 7 | 0
|  | Roof | 2 | 0 | 2 | Roof | 1 | 0
|  | Total | 127 | 83 |  | Total | 70 | 15
|  | Balance | 44 |  |  | Balance | 55
Delivery ONU
|  | Date | Qyt |  | Brand
|  | ??? | 3 | Mockup | commport
|  | 2026-02-27 | 15 | Resvivec by me | commport
|  | 2026-03-18 | 15 | Resvivec by me | commport
|  | 2026-04-04 | 24 | by sirivas | commport
|  | 2026-04-27 | 12 | Resvivec by me | bolein
|  | 2026-04-30 | 10 | Resvivec by me | bolein
|  | 2026-05-04 | 70 | Resvivec by me | commport
|  | 2026-06-04 | 62 | Resvivec by me | commport
|  | Delivered | 211
|  | Balance | -14

## Template
128 TOWER / Floor NO : | MPE Work Prograsse
Last Updadte : …./..../2026 | Time : ...:...
FlatNo/Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
[6 empty] | Data low Cuurent | 220v
01 1BHK
02 2BHK
03 2BHK
04 1BHK
05 2BHK
06 1BHK
07 Studio
08 studio
09 studio
10 studio
11 studio
12 1BHK
13 studio
14 studio
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations

## 128 TOWER - A -1st Floor
128 TOWER A / Floor NO : 1 | MPE Work Prograsse
Last Updadte : 18/06/2026 | Time :12.30 |  |  |  |  | 13
FlatNo/Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
[6 empty] | Data low Cuurent | 220v
101 2BHK | done | done | done | done | done |  | done | cabinet paint damage
102 2BHK | done | done | done | done | done |  | done
long spring cable pulling needed
103 1BHK | done | done | done | done | done |  | done
long spring cable pulling needed
104 1BHK | done | done | done | done | done |  | done
105 2BHK | done | done | done | done | done |  | done
106 1BHK | done | done | done | done | done |  | done | no inter come pipe
107 2BHK | done | done | done | done | done |  | done
108 studio | done | done | done | done | done |  | done
109 studio | done | done | done | done | done |  | done
110 studio | done | done | done | done | done |  | done
111 studio | done | done | done | done | done |  | done
112 1BHK | done | done | done | done | done |  | done
113 studio | done | done | done | done | done |  | done
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F1 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done
| 1st flr CAM 3 | stair1 |  | done |  | done | done
| 1st flr CAM 4 | stair2 |  | done |  | done | done
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding
| 1st flr CAM 7 | over view1 |  | done |  | done | done
| 1st flr CAM 8 | over view2 |  | done |  | done | done
| 1st flr CAM 9 | over view3 |  | done |  | done | done
| 1st flr CAM 10 | over view4 |  | done |  | done | done
| 1st flr CAM 11 | over view5 |  | done |  | done | done
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding
Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
Fiber Optic | [12 empty] | N/A
Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Fire System
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Home automations
Telephone
Data
Home automations
Home automations
Telephone
Data
Home automations
Home automations
Telephone
Data
Home automations
Home automations
Telephone
Data
Home automations
Home automations
Telephone
Data
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations

## 128 TOWER - A -2nd Floor
128 TOWER A / Floor No : 2 | MPE Work Prograsse
2026-04-22 | Time :12.30 |  |  |  | Total Num of completed flats : | 14
FlatNo/Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
[6 empty] | Data low Cuurent | 220v
201 1BHK | done | done | done | done | done |  | done
done
done
202 2BHK | done | done | done | done | done |  | done | long spring cable pulling needed
done
done
203 2BHK | done | done | done | done | done |  | done | long spring cable pulling needed
done
done
204 1BHK | done | done | done | done | done |  | done
done
done
205 2BHK | done | done | done | done | done |  | done
done
done
206 1BHK | done | done | pendding | done | done |  | done
done
done
207 Studio | done | done | done | done | done |  | done
done
done
208 studio | done | done | done | done | done |  | done
done
done
209 studio | done | done | done | done | done |  | done
done
done
210 studio | done | done | done | done | done |  | done
done
done
211 studio | done | done | done | done | done |  | done
done
done
212 1BHK | done | done | done | done | done |  | done
done
done
213 studio | done | done | done | done | done |  | done
done
done
214 studio | done | done | done | done | done |  | done
done
done
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F2 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done | [6 empty] | long spring needed
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done
Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
Fiber Optic
Inter Come | done | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | done | done | done | done | done | done | done | done
Fire System
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations
Home automations

## 128 Tower - A - 3nd Floor
128 TOWER A / Floor No : 3 | MPE Work Prograsse
2026-04-14 | Time :12.30 |  |  |  | Total Num of completed flats : | 14
FlatNo/Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
[6 empty] | Data low Cuurent | 220v
201 1BHK | done | done | done | done | done
202 2BHK | done | done | done | done | done
203 2BHK | done | done | done | done | done
204 1BHK | done | done | done | done | done
205 2BHK | done | done | done | done | done
206 1BHK | done | done | done | done | done
207 Studio | done | done | done | done | done
208 studio | done | done | done | done | done
209 studio | done | done | done | done | done
210 studio | done | done | done | done | done
211 studio | done | done | done | done | done
212 1BHK | done | done | done | done | done
213 studio | done | done | done | done | done
214 studio | done | done | done | done | done
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F3 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done | [6 empty] | long spring needed
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done
Flat Num | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314
Fiber Optic
Inter Come | done | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | done | done | done | done | done | done | done | done | done
Fire System
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations

## 128 Tower A - 4th Floor
128 TOWER B / Floor No : 1 | MPE Work Prograsse
2026-04-22 | Time :12.30 |  |  |  | Total Num of completed flats : | 0
FlatNo/Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
[6 empty] | Data low Cuurent | 220v
201 1BHK | done |  | done | done
202 2BHK | done |  | done | done
203 2BHK | done |  | done | done
204 1BHK | done |  | done | done | done
205 2BHK | done |  | done | done | done
206 1BHK | done |  | done | done | done
207 Studio | done |  | done | done | done
208 studio | done |  | done | done | done
209 studio | done |  | done | done | done
210 studio | done |  | done | done | done
211 studio | done |  | done | done | done
212 1BHK | done |  | done | done | done
213 studio | done |  | done | done | done
214 studio | done |  | done | done | done |  |  | Double wall pennding
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F4 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done | [6 empty] | long spring needed
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done
Flat Num | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414
Fiber Optic
Inter Come | done | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | done | done | done | done | done | done | done | done
Fire System
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations

## 128 TOWER - B -1st Floor
128 TOWER B / Floor No : 1 | MPE Work Prograsse
Last Updadte : 03/04/2026 | Time :12.30 |  |  |  | Total Num of completed flats : | 7
FlatNo/Type | Marking | DP/ONU Status |  | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
|  | DP/ | ONU |  |  |  | Data low Cuurent | 220v
101 1BHK | done | done | done | done | unfinished |  |  |  | civil work pendding in bedroom
bed room no services yet (need cutting - backbox- piping )
102 2BHK | done | done | done | done | done | done
sokets in bed roon are pendding
103 2BHK | done | done | done | done | done | done |  |  | civil work pendding
104 1BHK | done | done | done | done | done | done |  |  | civil work in bed room
105 2BHK | done | done | done | done | done | done |  |  | close the previous intercome and keybad in hall
106 1BHK | done | done | done | done | done | done |  |  | No service in bedroom
107 2BHK | done | done | done | done | done | done |  |  | Civil work in Hall pendding
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations

## 128 TOWER -B - 2 Floor
128 TOWER B / Floor No : 2 | MPE Work Prograsse
Last Updadte : 03/04/2026 | Time :12.30 |  |  |  | Total Num of completed flats : | 8
FlatNo/Type | Marking | DP/ONU Status |  | Cutting | wall Back box socket | Pipe | Wireing |  | Nots
|  | DP | ONU |  |  |  | Data low Cuurent | 220v
201 1BHK | done | done |  | done | done | done |  |  | Bedroom cabinet light and hairdryer backbox missing
202 2BHK | done | done |  | done | done | done |  |  | intercone need to shift to corridor side
Bedroom cabinet ligh
203 2BHK | done | done |  | done | done | done |  |  | washing machine back box and pipe messing
204 1BHK | done | done |  | done | done | done
205 2BHK | done | done |  | done | done | done |  |  | bedroom right (Keybad - data ) need to swap
206 1BHK | done | done |  | done | done | done
207 2BHK | done | done |  | done | done | done |  |  | socket under DP missing, Block work in living room
208 2BHK | done | done |  | done | done | done |  |  | socket balance in hall
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Data
Home automations
Telephone
Telephone
Data
Telephone
Data
Home automations

## ELV_128_Tower A_B1
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-B1 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | B1 CAM 1 | STAIR 2 | 120% ID VIEW | done |  | done | done
| B1 CAM 2 | STAIR 1 | 120% ID VIEW | done |  | done | done
| B1 CAM 3 | ENTRY-1 | 25% OBS VIEW | done |  | done | done
| B1 CAM 4 | ENTRY-2 | 120% ID VIEW | done |  | done | done
| B1 CAM 5 | LIFT LOBBY-1 | 25% OBS VIEW | done |  | done | done
| B1 CAM 6 | LIFT LOBBY-2 | 120% ID VIEW | done |  | done | done
| B1 CAM 7 | VIEW-1 | 10% DET VIEW | done |  | done | done
| B1 CAM 8 | VIEW-2 | 10% DET VIEW | done |  | done | done
| B1 CAM 9 | RAMP1 | 120% ID VIEW | done |  | done | done
| B1 CAM 10 | DRIVE WAY1 | 10% DET VIEW | done |  | done | done
| B1 CAM 11 | DRIVE WAY2 | 10% DET VIEW | done |  | done | done
| B1 CAM 12 | DRIVE WAY3 | 10% DET VIEW | done |  | done | done
| B1 CAM 13 | DRIVE WAY4 | 10% DET VIEW | done |  | done | done
| B1 CAM 14 | DRIVE WAY5 | 120% ID VIEW | done |  | done | done
| B1 CAM 15 | RAMP2 | 10% DET VIEW | done |  | done | done
Access Control | CR: Card Reader | Lift lobby 1
| ML: Magnetic Lock (القفل المغناطيسي) | Lift lobby 2
| DRC: Door Release/Contact (جهاز إطلاق/اتصال الباب) | Lift lobby 3
| DC: Door Contact (مستشعر حالة الباب) | Lift lobby 4
| JB: Junction Box (صندوق التوصيل) | Lift lobby 5
| DB: Distribution Board (لوحة التوزيع) | Lift lobby 6
| LC: Lock Controller (متحكم القفل) | Lift lobby 7
| CR: Card Reader | Stiar-2
| ML: Magnetic Lock (القفل المغناطيسي) | Stiar-3
| DC: Door Contact (مستشعر حالة الباب) | Stiar-4
| JB: Junction Box (صندوق التوصيل) | Stiar-5
| DB: Distribution Board (لوحة التوزيع) | Stiar-6
Inter Come
Fire System

## ELV_128_TowerA_F1
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F1 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done
| 1st flr CAM 3 | stair1 |  | done |  | done | done
| 1st flr CAM 4 | stair2 |  | done |  | done | done
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding
| 1st flr CAM 7 | over view1 |  | done |  | done | done
| 1st flr CAM 8 | over view2 |  | done |  | done | done
| 1st flr CAM 9 | over view3 |  | done |  | done | done
| 1st flr CAM 10 | over view4 |  | done |  | done | done
| 1st flr CAM 11 | over view5 |  | done |  | done | done
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding
Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
Fiber Optic | [12 empty] | N/A
Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Fire System

## ELV_128_TowerA_F2
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F2 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done
Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
Fiber Optic
Inter Come | done | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | done | done | pendding | pendding | pendding | pendding | pendding | pendding
Fire System

## ELV_128_TowerB_B1
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-B-B1 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | b1 CAM 1 | STAIR-1 | 120% IDENTIFICATION VIEW | done |  | Not Avalibale
| b1 CAM 2 | STAIR-2 | 120% IDENTIFICATION VIEW | done |  | done | done
| b1 CAM 3 | ENTRY-1 | 120% IDENTIFICATION VIEW | done |  | done | done
| b1 CAM 4 | ENTRY-2 | 120% IDENTIFICATION VIEW | done |  | done | done
| b1 CAM 5 | LIFT LOBY-1 | 25% OBSERVATION VIEW | done |  | done | done
| b1 CAM 6 | LIFT LOBY-2 | 25% OBSERVATION VIEW | done |  | done | done
| b1 CAM 7 | LOBY | 10% DETECTION VIEW | done |  | done | done
| b1 CAM 8 | DRIVE WAY 1 | 10% DETECTION VIEW | done |  | Blocked pipeline
| b1 CAM 9 | DRIVE WAY 2 | 10% DETECTION VIEW | done |  | done | done
| b1 CAM 10 | DRIVE WAY 2 | 10% DETECTION VIEW | done |  | done | done
| b1 CAM 11 | DRIVE WAY 2 | 10% DETECTION VIEW | done |  | done | done
Access Control | CR: Card Reader | Lift lobby 1
| ML: Magnetic Lock (القفل المغناطيسي) | Lift lobby 2
| DRC: Door Release/Contact (جهاز إطلاق/اتصال الباب) | Lift lobby 3
| DC: Door Contact (مستشعر حالة الباب) | Lift lobby 4
| JB: Junction Box (صندوق التوصيل) | Lift lobby 5
| DB: Distribution Board (لوحة التوزيع) | Lift lobby 6
| LC: Lock Controller (متحكم القفل) | Lift lobby 7
| CR: Card Reader | Stiar-2
| ML: Magnetic Lock (القفل المغناطيسي) | Stiar-3
| DC: Door Contact (مستشعر حالة الباب) | Stiar-4
| JB: Junction Box (صندوق التوصيل) | Stiar-5
| DB: Distribution Board (لوحة التوزيع) | Stiar-6
Flat Num
Fiber Optic
Inter Come
Fire System

## deepseek_csv_20260429_e553a1
ELV system |  | Point |  | Phase | [7 empty] | Floor | Completed works | Nots
128-A-F1 |  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done
| 1st flr CAM 3 | stair1 |  | done |  | done | done
| 1st flr CAM 4 | stair2 |  | done |  | done | done
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding
| 1st flr CAM 7 | over view1 |  | done |  | done | done
| 1st flr CAM 8 | over view2 |  | done |  | done | done
| 1st flr CAM 9 | over view3 |  | done |  | done | done
| 1st flr CAM 10 | over view4 |  | done |  | done | done
| 1st flr CAM 11 | over view5 |  | done |  | done | done
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding
Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
Fiber Optic | [12 empty] | N/A
Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Fire System