## Flats
TOWER |  |  | A | ELV Flats Work Prograsse
Last Updadte : |  |  | 25/06/2026
Time : |  |  | 12.3
FlatNo | Floor number | tower | Type | Marking | DP/ONU Status | Cutting | wall Back box socket | Ground Pipe | Pipe | Wireing |  |  |  | Nots
[10 empty] | Data | intercome | Home Automations | 220v
1
101 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done | cabinet paint damage
102 |  |  | 2BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
103 |  |  | 1BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
104 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
105 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
106 |  |  | 1BHK | done | done | done | done | done | done | done | pending | done | done | no inter come pipe
107 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
108 |  |  | studio | done | done | done | done | done | done | done | done | done | done
109 |  |  | studio | done | done | done | done | done | done | done | done | done | done
110 |  |  | studio | done | done | done | done | done | done | done | done | done | done
111 |  |  | studio | done | done | done | done | done | done | done | done | done | done
112 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
113 |  |  | studio | done | done | done | done | done | done | done | done | done | done
2
201 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
202 |  |  | 2BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
203 |  |  | 1BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
204 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
205 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
206 |  |  | 1BHK | done | done | done | done | done | done | done | pending | done | done | no inter come pipe
207 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
208 |  |  | studio | done | done | done | done | done | done | done | done | done | done
209 |  |  | studio | done | done | done | done | done | done | done | done | done | done
210 |  |  | studio | done | done | done | done | done | done | done | done | done | done
211 |  |  | studio | done | done | done | done | done | done | done | done | done | done
212 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
213 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
214 |  |  | studio | done | done | done | done | done | done | done | done | done | done
3
301 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
302 |  |  | 2BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
303 |  |  | 1BHK | done | done | done | done | done | done | done | pending | done | done | long spring cable pulling needed
304 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
305 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
306 |  |  | 1BHK | done | done | done | done | done | done | done | pending | done | done
307 |  |  | 2BHK | done | done | done | done | done | done | done | done | done | done
308 |  |  | studio | done | done | done | done | done | done | done | done | done | done
309 |  |  | studio | done | done | done | done | done | done | done | done | done | done
310 |  |  | studio | done | done | done | done | done | done | done | done | done | done
311 |  |  | studio | done | done | done | done | done | done | done | done | done | done
312 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
313 |  |  | 1BHK | done | done | done | done | done | done | done | done | done | done
314 |  |  | studio | done | done | done | done | done | done | done | done | done | done
4
401 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
402 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
403 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
404 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
405 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
406 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
407 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
408 |  |  | studio | done | done | done | done |  | done |  |  | done | done
409 |  |  | studio | done | done | done | done |  | done |  |  | done | done
410 |  |  | studio | done | done | done | done |  | done |  |  | done | done
411 |  |  | studio | done | done | done | done |  | done |  |  | done | done
412 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
413 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
414 |  |  | studio | done | done | done | done |  | done |  |  | done | done
5
501 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
502 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
503 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
504 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
505 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
506 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
507 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
508 |  |  | studio | done | done | done | done |  | done |  |  | done | done
509 |  |  | studio | done | done | done | done |  | done |  |  | done | done
510 |  |  | studio | done | done | done | done |  | done |  |  | done | done
511 |  |  | studio | done | done | done | done |  | done |  |  | done | done
512 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
513 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
514 |  |  | studio | done | done | done | done |  | done |  |  | done | done
6
601 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
602 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
603 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
604 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
605 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
606 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
607 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
608 |  |  | studio | done | done | done | done |  | done |  |  | done | done
609 |  |  | studio | done | done | done | done |  | done |  |  | done | done
610 |  |  | studio | done | done | done | done |  | done |  |  | done | done
611 |  |  | studio | done | done | done | done |  | done |  |  | done | done
612 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
613 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
614 |  |  | studio | done | done | done | done |  | done |  |  | done | done
7
701 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
702 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
703 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
long spring cable pulling needed
704 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
705 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
706 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
707 |  |  | 2BHK | done | done | done | done |  | done |  |  | done | done
708 |  |  | studio | done | done | done | done |  | done |  |  | done | done
709 |  |  | studio | done | done | done | done |  | done |  |  | done | done
710 |  |  | studio | done | done | done | done |  | done |  |  | done | done
711 |  |  | studio | done | done | done | done |  | done |  |  | done | done
712 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
713 |  |  | 1BHK | done | done | done | done |  | done |  |  | done | done
714 |  |  | studio | done | done | done | done |  | done |  |  | done | done
8
801 |  |  | 2BHK | done |  | done
802 |  |  | 2BHK | done |  | done
long spring cable pulling needed
803 |  |  | 1BHK | done |  | done
long spring cable pulling needed
804 |  |  | 1BHK | done |  | done
805 |  |  | 2BHK | done |  | done
806 |  |  | 1BHK | done |  | done
807 |  |  | 2BHK | done |  | done
808 |  |  | studio | done |  | done
809 |  |  | studio | done |  | done
810 |  |  | studio | done |  | done
811 |  |  | studio | done |  | done
812 |  |  | 1BHK | done |  | done
813 |  |  | 1BHK | done |  | done
814 |  |  | studio | done |  | done
9
901 |  |  | 2BHK
902 |  |  | 2BHK
903 |  |  | 1BHK
904 |  |  | 1BHK
905 |  |  | 2BHK
906 |  |  | 1BHK
907 |  |  | 2BHK
908 |  |  | studio
909 |  |  | studio
910 |  |  | studio
911 |  |  | studio
912 |  |  | 1BHK
913 |  |  | 1BHK
914 |  |  | studio
Roof

## Floors
TOWER | A | ELV Floors Work Prograsse
Last Updadte : | 25/06/2026
Time : | 12.3
ELV system | Point | Location | Additional details | Phase | [7 empty] | Floor | Completed works | Nots
|  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
Bassment 1
CCTV | B1 CAM 1 | STAIR 2 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 1
| B1 CAM 2 | STAIR 1 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 2
| B1 CAM 3 | ENTRY-1 | 25% OBS VIEW | done |  | done | done |  |  |  |  | Bassment 3
| B1 CAM 4 | ENTRY-2 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 4
| B1 CAM 5 | LIFT LOBBY-1 | 25% OBS VIEW | done |  | done | done |  |  |  |  | Bassment 5
| B1 CAM 6 | LIFT LOBBY-2 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 6
| B1 CAM 7 | VIEW-1 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 7
| B1 CAM 8 | VIEW-2 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 8
| B1 CAM 9 | RAMP1 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 9
| B1 CAM 10 | DRIVE WAY1 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 10
| B1 CAM 11 | DRIVE WAY2 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 11
| B1 CAM 12 | DRIVE WAY3 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 12
| B1 CAM 13 | DRIVE WAY4 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 13
| B1 CAM 14 | DRIVE WAY5 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 14
| B1 CAM 15 | RAMP2 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 15
Access Control | CR: Card Reader | Lift lobby 1 | [9 empty] | Bassment 16
| ML: Magnetic Lock (القفل المغناطيسي) | Lift lobby 2 | [9 empty] | Bassment 17
| DRC: Door Release/Contact (جهاز إطلاق/اتصال الباب) | Lift lobby 3 | [9 empty] | Bassment 18
| DC: Door Contact (مستشعر حالة الباب) | Lift lobby 4 | [9 empty] | Bassment 19
| JB: Junction Box (صندوق التوصيل) | Lift lobby 5 | [9 empty] | Bassment 20
| DB: Distribution Board (لوحة التوزيع) | Lift lobby 6 | [9 empty] | Bassment 21
| LC: Lock Controller (متحكم القفل) | Lift lobby 7 | [9 empty] | Bassment 22 |  |  |  | Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
| CR: Card Reader | Stiar-2 | [9 empty] | Bassment 23 |  |  |  | Fiber Optic | 214: N/A
| ML: Magnetic Lock (القفل المغناطيسي) | Stiar-3 | [9 empty] | Bassment 24
| DC: Door Contact (مستشعر حالة الباب) | Stiar-4 | [9 empty] | Bassment 25
| JB: Junction Box (صندوق التوصيل) | Stiar-5 | [9 empty] | Bassment 26
| DB: Distribution Board (لوحة التوزيع) | Stiar-6 | [9 empty] | Bassment 27 |  |  |  | Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Bassment 2
CCTV | [11 empty] | Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Access Control | [11 empty] | Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Ground Floor
CCTV | [11 empty] | Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Access Control | [11 empty] | Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Gate Barrier | [11 empty] | Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
poduim Floor
CCTV | [11 empty] | poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
Access Control | [11 empty] | poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
Gate Barrier | [11 empty] | poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
1 St floor
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 3 | stair1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 4 | stair2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 7 | over view1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 8 | over view2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 9 | over view3 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 10 | over view4 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 11 | over view5 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
intercom | 101 |  |  | done |  | done | [5 empty] | 1
| 102 |  |  | done |  | done | pendding |  |  |  |  | 1
| 103 |  |  | done |  | done | pendding |  |  |  |  | 1
| 104 |  |  | done |  | done | [5 empty] | 1
| 105 |  |  | done |  | done | [5 empty] | 1
| 106 |  |  | done |  | pendding | pendding |  |  |  |  | 1
| 107 |  |  | done |  | done | [5 empty] | 1
| 108 |  |  | done |  | done | [5 empty] | 1
| 109 |  |  | done |  | done | [5 empty] | 1
| 110 |  |  | done |  | done | [5 empty] | 1
| 111 |  |  | done |  | done | [5 empty] | 1
| 112 |  |  | done |  | done | [5 empty] | 1
| 113 |  |  | done |  | done | [5 empty] | 1
Fiber Optic | 101 | [10 empty] | 1
| 102 | [10 empty] | 1
| 103 | [10 empty] | 1
| 104 | [10 empty] | 1
| 105 | [10 empty] | 1
| 106 | [10 empty] | 1
| 107 | [10 empty] | 1
| 108 | [10 empty] | 1
| 109 | [10 empty] | 1
| 110 | [10 empty] | 1
| 111 | [10 empty] | 1
| 112 | [10 empty] | 1
| 113 | [10 empty] | 1
2nd Floor
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2 |  |  | pendding Long spring cable pulling required
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 2 |  |  | pendding Long spring cable pulling required
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
intercom | 201 |  |  | done |  | done | [5 empty] | 2
| 202 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 203 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 204 |  |  | done |  | done | done |  |  |  |  | 2
| 205 |  |  | done |  | done | done |  |  |  |  | 2
| 206 |  |  | done |  | done | done |  |  |  |  | 2
| 207 |  |  | done |  | done | done |  |  |  |  | 2
| 208 |  |  | done |  | done | done |  |  |  |  | 2
| 209 |  |  | done |  | done | done |  |  |  |  | 2
| 210 |  |  | done |  | done | done |  |  |  |  | 2
| 211 |  |  | done |  | done | done |  |  |  |  | 2
| 212 |  |  | done |  | done | done |  |  |  |  | 2
| 213 |  |  | done |  | done | done |  |  |  |  | 2
| 214 |  |  | done |  | done | done |  |  |  |  | 2
Fiber Optic | 201 |  |  | done | [7 empty] | 2
| 202 |  |  | done | [7 empty] | 2
| 203 |  |  | done | [7 empty] | 2
| 204 |  |  | done | [7 empty] | 2
| 205 |  |  | done | [7 empty] | 2
| 206 |  |  | done | [7 empty] | 2
| 207 |  |  | done | [7 empty] | 2
| 208 |  |  | done | [7 empty] | 2
| 209 |  |  | done | [7 empty] | 2
| 210 |  |  | done | [7 empty] | 2
| 211 |  |  | done | [7 empty] | 2
| 212 |  |  | done | [7 empty] | 2
| 213 |  |  | done | [7 empty] | 2
| 214 |  |  | done | [7 empty] | 2
3nd Floor
CCTV | 3nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 3
| 3nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
intercom | 301 |  |  | done |  | done | [5 empty] | 3
| 302 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 303 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 304 |  |  | done |  | done | done |  |  |  |  | 3
| 305 |  |  | done |  | done | done |  |  |  |  | 3
| 306 |  |  | done |  | done | done |  |  |  |  | 3
| 307 |  |  | done |  | done | done |  |  |  |  | 3
| 308 |  |  | done |  | done | done |  |  |  |  | 3
| 309 |  |  | done |  | done | done |  |  |  |  | 3
| 310 |  |  | done |  | done | done |  |  |  |  | 3
| 311 |  |  | done |  | done | done |  |  |  |  | 3
| 312 |  |  | done |  | done | done |  |  |  |  | 3
| 313 |  |  | done |  | done | done |  |  |  |  | 3
| 314 |  |  | done |  | done | done |  |  |  |  | 3
Fiber Optic | 301 |  |  | done | [7 empty] | 3
| 302 |  |  | done | [7 empty] | 3
| 303 |  |  | done | [7 empty] | 3
| 304 |  |  | done | [7 empty] | 3
| 305 |  |  | done | [7 empty] | 3
| 306 |  |  | done | [7 empty] | 3
| 307 |  |  | done | [7 empty] | 3
| 308 |  |  | done | [7 empty] | 3
| 309 |  |  | done | [7 empty] | 3
| 310 |  |  | done | [7 empty] | 3
| 311 |  |  | done | [7 empty] | 3
| 312 |  |  | done | [7 empty] | 3
| 313 |  |  | done | [7 empty] | 3
| 314 |  |  | done | [7 empty] | 3
4th Floor
CCTV | 4nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 4
| 4nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | pending |  |  |  |  | 4 |  | long spring needed
| 4nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
4
Inter Come | 401 |  |  | done | done | done | done |  |  |  |  | 4
| 402 | [5 empty] | done |  |  |  |  | 4
| 403 | [5 empty] | pending |  |  |  |  | 4
| 404 | done |  |  |  |  | pending |  |  |  |  | 4
| 405 | done |  | done |  | done | done |  |  |  |  | 4
| 406 | done |  | done |  | done | done |  |  |  |  | 4
| 407 | done |  | done |  | done | done |  |  |  |  | 4
| 408 | done |  | done |  | done | done |  |  |  |  | 4
| 409 | done |  | done |  | done | done |  |  |  |  | 4
| 410 | done |  | done |  | done | done |  |  |  |  | 4
| 411 | done |  | done |  | done | done |  |  |  |  | 4
| 412 | done |  | done |  | done | done |  |  |  |  | 4
| 413 | done |  | done |  | done | done |  |  |  |  | 4
| 414 | done |  | done |  | done | done |  |  |  |  | 4
| 415 | done |  | done |  | done | done |  |  |  |  | 4