## Flats
Project Code |  | 121
Project Name |  | Alwaleed
Project Location |  | Nad-alshaba
Last Update : |  | 26/09/2026
Flat Number | Tower | Floor Number | Type | DP/ONU Status | Ground Pipe | Wall Pipe | Data |  | Intercom |  | Home Automation |  | SAMATV |  | FTTH |  | Nots | Total Status
[7 empty] | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing
long spring cable pulling needed
long spring cable pulling needed
long spring cable pulling needed
long spring cable pulling needed
long spring cable pulling needed
long spring cable pulling needed
long spring cable pulling needed
long spring cable pulling needed
[7 empty] | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing
101 |  | 1 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  | cabinet paint damage | completed
102 |  | 1 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  | long spring cable pulling needed | completed
103 |  | 1 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  | long spring cable pulling needed | completed
104 |  | 1 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
105 |  | 1 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
106 |  | 1 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  | no inter come pipe | completed
107 |  | 1 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
108 |  | 1 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
109 |  | 1 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
110 |  | 1 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
111 |  | 1 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
112 |  | 1 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
113 |  | 1 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
201 |  | 2 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
202 |  | 2 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  | long spring cable pulling needed | completed
203 |  | 2 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  | long spring cable pulling needed | completed
204 |  | 2 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
205 |  | 2 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A | done |  |  | completed
206 |  | 2 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
207 |  | 2 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
208 |  | 2 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
209 |  | 2 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
210 |  | 2 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
211 |  | 2 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
212 |  | 2 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
213 |  | 2 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections to elv room' | completed
214 |  | 2 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | completed
301 |  | 3 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
302 |  | 3 | 2BHK | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  | long spring cable pulling needed | in progress
303 |  | 3 | 1BHK | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  | long spring cable pulling needed | in progress
304 |  | 3 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
305 |  | 3 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
306 |  | 3 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
307 |  | 3 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
308 |  | 3 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
309 |  | 3 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
310 |  | 3 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
311 |  | 3 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
312 |  | 3 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
313 |  | 3 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
314 |  | 3 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
401 |  | 4 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | in progress
402 |  | 4 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
403 |  | 4 | 1BHK | done | done | done | done |  |  |  | done | done | N/A | N/A |  |  |  | in progress
404 |  | 4 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
405 |  | 4 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
406 |  | 4 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | #REF!
407 |  | 4 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | #REF!
408 |  | 4 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
409 |  | 4 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
410 |  | 4 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
411 |  | 4 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
412 |  | 4 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
413 |  | 4 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
414 |  | 4 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  | intercom need connections from main pipe to socket | #REF!
501 |  | 5 | 2BHK | done | pending | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
502 |  | 5 | 2BHK | done | pending | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
503 |  | 5 | 1BHK | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
504 |  | 5 | 1BHK | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
505 |  | 5 | 2BHK | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
506 |  | 5 | 1BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | #REF!
507 |  | 5 | 2BHK | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | in progress
508 |  | 5 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | #REF!
509 |  | 5 | studio | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
510 |  | 5 | studio | done | done | done | done |  | done |  | done | done | N/A | N/A |  |  |  | #REF!
511 |  | 5 | studio | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | in progress
512 |  | 5 | 1BHK | done | pending | done | no pipe |  | pending |  | done | done | N/A | N/A |  |  |  | #REF!
513 |  | 5 | 1BHK | done | pending | done | pending |  | pending |  | done | done | N/A | N/A |  |  |  | completed
514 |  | 5 | studio | done | done | done | done |  | pending |  | done | done | N/A | N/A |  |  |  | #REF!
601 |  | 6 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
602 |  | 6 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
603 |  | 6 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
604 |  | 6 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
605 |  | 6 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
606 |  | 6 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
607 |  | 6 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
608 |  | 6 | studio | done |  | done |  |  |  |  | done | done | N/A | N/A |  |  |  | in progress
609 |  | 6 | studio | done |  | done | done |  |  |  | done | done | N/A | N/A |  |  |  | in progress
610 |  | 6 | studio | done |  | done | done |  |  |  | done | done | N/A | N/A |  |  |  | in progress
611 |  | 6 | studio | done |  | done | done |  |  |  | done | done | N/A | N/A |  |  |  | in progress
612 |  | 6 | 1BHK | done | done | done | done |  |  |  | done | done | N/A | N/A |  |  |  | in progress
613 |  | 6 | 1BHK | done | done | done | civil work pending |  |  |  | done | done | N/A | N/A |  |  |  | completed
614 |  | 6 | studio | done |  | done | done |  |  |  | done | done | N/A | N/A |  |  |  | in progress
701 |  | 7 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
702 |  | 7 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
703 |  | 7 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
704 |  | 7 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
705 |  | 7 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
706 |  | 7 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
707 |  | 7 | 2BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
708 |  | 7 | studio | done |  | done |  |  |  |  | done | done | N/A | N/A
709 |  | 7 | studio | done |  | done |  |  |  |  | done | done | N/A | N/A
710 |  | 7 | studio | done |  | done |  |  |  |  | done | done | N/A | N/A
711 |  | 7 | studio | done |  | done |  |  |  |  | done | done | N/A | N/A
712 |  | 7 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
713 |  | 7 | 1BHK | done |  | done |  |  |  |  | done | done | N/A | N/A
714 |  | 7 | studio | done |  | done |  |  |  |  | done | done | N/A | N/A
801 |  | 8 | 2BHK | [9 empty] | N/A | N/A
802 |  | 8 | 2BHK | [9 empty] | N/A | N/A
803 |  | 8 | 1BHK | [9 empty] | N/A | N/A
804 |  | 8 | 1BHK | [9 empty] | N/A | N/A
805 |  | 8 | 2BHK | [9 empty] | N/A | N/A
806 |  | 8 | 1BHK | [9 empty] | N/A | N/A
807 |  | 8 | 2BHK | [9 empty] | N/A | N/A
808 |  | 8 | studio | [9 empty] | N/A | N/A
809 |  | 8 | studio | [9 empty] | N/A | N/A
810 |  | 8 | studio | [9 empty] | N/A | N/A
811 |  | 8 | studio | [9 empty] | N/A | N/A
812 |  | 8 | 1BHK | [9 empty] | N/A | N/A
813 |  | 8 | 1BHK | [9 empty] | N/A | N/A
814 |  | 8 | studio | [9 empty] | N/A | N/A
901 |  | 9 | 2BHK | [9 empty] | N/A | N/A
902 |  | 9 | 2BHK | [9 empty] | N/A | N/A
903 |  | 9 | 1BHK | [9 empty] | N/A | N/A
904 |  | 9 | 1BHK | [9 empty] | N/A | N/A
905 |  | 9 | 2BHK | [9 empty] | N/A | N/A
906 |  | 9 | 1BHK | [9 empty] | N/A | N/A
907 |  | 9 | 2BHK | [9 empty] | N/A | N/A
908 |  | 9 | studio | [9 empty] | N/A | N/A
909 |  | 9 | studio | [9 empty] | N/A | N/A
910 |  | 9 | studio | [9 empty] | N/A | N/A
911 |  | 9 | studio | [9 empty] | N/A | N/A
912 |  | 9 | 1BHK | [9 empty] | N/A | N/A
913 |  | 9 | 1BHK | [9 empty] | N/A | N/A
914 |  | 9 | studio | [9 empty] | N/A | N/A

## Floors
TOWER | A | ELV Floors Work Prograsse
Last Updadte : | 25/06/2026
Time : | 12.3
ELV system | Point | Location | Additional details | Phase | [7 empty] | Floor | Completed works | Nots
|  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
Bassment 1
CCTV | B1 CAM 1 | STAIR 2 | 120% ID VIEW | done |  | done | done
| B1 CAM 2 | STAIR 1 | 120% ID VIEW | done |  | done | done
| B1 CAM 3 | ENTRY-1 | 25% OBS VIEW | done |  | done | done
| B1 CAM 4 | ENTRY-2 | 120% ID VIEW | done |  | done | done
| B1 CAM 5 | LIFT LOBBY-1 | 25% OBS VIEW | done |  | done | done
| B1 CAM 6 | LIFT LOBBY-2 | 120% ID VIEW | done |  | done | done
| B1 CAM 7 | VIEW-1 | 10% DET VIEW | done |  | done | done
| B1 CAM 8 | VIEW-2 | 10% DET VIEW | done |  | done | done
| B1 CAM 9 | RAMP1 | 120% ID VIEW | done |  | done | done
| B1 CAM 10 | DRIVE WAY1 | 10% DET VIEW | done |  | done | done
| B1 CAM 11 | DRIVE WAY2 | 10% DET VIEW | done |  | done | done
| B1 CAM 12 | DRIVE WAY3 | 10% DET VIEW | done |  | done | done
| B1 CAM 13 | DRIVE WAY4 | 10% DET VIEW | done |  | done | done
| B1 CAM 14 | DRIVE WAY5 | 120% ID VIEW | done |  | done | done
| B1 CAM 15 | RAMP2 | 10% DET VIEW | done |  | done | done
Access Control | CR: Card Reader | Lift lobby 1
| ML: Magnetic Lock (القفل المغناطيسي) | Lift lobby 2
| DRC: Door Release/Contact (جهاز إطلاق/اتصال الباب) | Lift lobby 3
| DC: Door Contact (مستشعر حالة الباب) | Lift lobby 4
| JB: Junction Box (صندوق التوصيل) | Lift lobby 5
| DB: Distribution Board (لوحة التوزيع) | Lift lobby 6
| LC: Lock Controller (متحكم القفل) | Lift lobby 7 | [13 empty] | Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
| CR: Card Reader | Stiar-2 | [13 empty] | Fiber Optic | 214: N/A
| ML: Magnetic Lock (القفل المغناطيسي) | Stiar-3
| DC: Door Contact (مستشعر حالة الباب) | Stiar-4
| JB: Junction Box (صندوق التوصيل) | Stiar-5
| DB: Distribution Board (لوحة التوزيع) | Stiar-6 | [13 empty] | Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Bassment 2
CCTV
Access Control
Ground Floor
CCTV
Access Control
Gate Barrier
poduim Floor
CCTV
Access Control
Gate Barrier
1 St floor
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 3 | stair1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 4 | stair2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 7 | over view1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 8 | over view2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 9 | over view3 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 10 | over view4 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 11 | over view5 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
intercom | 101 |  |  | done |  | done | [5 empty] | 1
| 102 |  |  | done |  | done | pendding |  |  |  |  | 1
| 103 |  |  | done |  | done | pendding |  |  |  |  | 1
| 104 |  |  | done |  | done | [5 empty] | 1
| 105 |  |  | done |  | done | [5 empty] | 1
| 106 |  |  | done |  | pendding | pendding |  |  |  |  | 1
| 107 |  |  | done |  | done | [5 empty] | 1
| 108 |  |  | done |  | done | [5 empty] | 1
| 109 |  |  | done |  | done | [5 empty] | 1
| 110 |  |  | done |  | done | [5 empty] | 1
| 111 |  |  | done |  | done | [5 empty] | 1
| 112 |  |  | done |  | done | [5 empty] | 1
| 113 |  |  | done |  | done | [5 empty] | 1
Fiber Optic | 101 | [10 empty] | 1
| 102 | [10 empty] | 1
| 103 | [10 empty] | 1
| 104 | [10 empty] | 1
| 105 | [10 empty] | 1
| 106 | [10 empty] | 1
| 107 | [10 empty] | 1
| 108 | [10 empty] | 1
| 109 | [10 empty] | 1
| 110 | [10 empty] | 1
| 111 | [10 empty] | 1
| 112 | [10 empty] | 1
| 113 | [10 empty] | 1
2nd Floor
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2 |  |  | pendding Long spring cable pulling required
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 2 |  |  | pendding Long spring cable pulling required
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
intercom | 201 |  |  | done |  | done | [5 empty] | 2
| 202 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 203 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 204 |  |  | done |  | done | done |  |  |  |  | 2
| 205 |  |  | done |  | done | done |  |  |  |  | 2
| 206 |  |  | done |  | done | done |  |  |  |  | 2
| 207 |  |  | done |  | done | done |  |  |  |  | 2
| 208 |  |  | done |  | done | done |  |  |  |  | 2
| 209 |  |  | done |  | done | done |  |  |  |  | 2
| 210 |  |  | done |  | done | done |  |  |  |  | 2
| 211 |  |  | done |  | done | done |  |  |  |  | 2
| 212 |  |  | done |  | done | done |  |  |  |  | 2
| 213 |  |  | done |  | done | done |  |  |  |  | 2
| 214 |  |  | done |  | done | done |  |  |  |  | 2
Fiber Optic | 201 |  |  | done
| 202 |  |  | done
| 203 |  |  | done
| 204 |  |  | done
| 205 |  |  | done
| 206 |  |  | done
| 207 |  |  | done
| 208 |  |  | done
| 209 |  |  | done
| 210 |  |  | done
| 211 |  |  | done
| 212 |  |  | done
| 213 |  |  | done
| 214 |  |  | done
3nd Floor
CCTV | 3nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 3nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 3nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
| 3nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 2
| 3nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 3nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 3nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
| 3nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
intercom | 301 |  |  | done |  | done | [5 empty] | 2
| 302 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 303 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 304 |  |  | done |  | done | done |  |  |  |  | 2
| 305 |  |  | done |  | done | done |  |  |  |  | 2
| 306 |  |  | done |  | done | done |  |  |  |  | 2
| 307 |  |  | done |  | done | done |  |  |  |  | 2
| 308 |  |  | done |  | done | done |  |  |  |  | 2
| 309 |  |  | done |  | done | done |  |  |  |  | 2
| 310 |  |  | done |  | done | done |  |  |  |  | 2
| 311 |  |  | done |  | done | done |  |  |  |  | 2
| 312 |  |  | done |  | done | done |  |  |  |  | 2
| 313 |  |  | done |  | done | done |  |  |  |  | 2
| 314 |  |  | done |  | done | done |  |  |  |  | 2
Fiber Optic | 301 |  |  | done
| 302 |  |  | done
| 303 |  |  | done
| 304 |  |  | done
| 305 |  |  | done
| 306 |  |  | done
| 307 |  |  | done
| 308 |  |  | done
| 309 |  |  | done
| 310 |  |  | done
| 311 |  |  | done
| 312 |  |  | done
| 313 |  |  | done
| 314 |  |  | done
4th Floor
CCTV | 4nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done
| 4nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done
| 4nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done
| 4nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done
| 4nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | pending | [6 empty] | long spring needed
| 4nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done
| 4nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done
| 4nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done
Inter Come | 401 |  |  | done | done | done | done
| 402 | [5 empty] | done
| 403 | [5 empty] | pending
| 404 | done |  |  |  |  | pending
| 405 | done |  | done |  | done | done |  |  |  |  | 2
| 406 | done |  | done |  | done | done |  |  |  |  | 2
| 407 | done |  | done |  | done | done |  |  |  |  | 2
| 408 | done |  | done |  | done | done |  |  |  |  | 2
| 409 | done |  | done |  | done | done |  |  |  |  | 2
| 410 | done |  | done |  | done | done |  |  |  |  | 2
| 411 | done |  | done |  | done | done |  |  |  |  | 2
| 412 | done |  | done |  | done | done |  |  |  |  | 2
| 413 | done |  | done |  | done | done |  |  |  |  | 2
| 414 | done |  | done |  | done | done |  |  |  |  | 2
| 415 | done |  | done |  | done | done |  |  |  |  | 2