## Flats
Project Code |  | 120
Project Name
Project Location |  | JVC
Last Updadte : |  | 30/6/2026
Floor Num |  | 10L+1roof+2Bassment
Flat Number | Tower | Floor number | Type | DP/ONU Status | Ground Pipe | Wall Pipe | Data |  | Intercom |  | Home Automation |  | SAMATV |  | FTTH |  | Nots
[7 empty] | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing | Wiring | Outlet Fixing
101 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
102 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
103 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
104 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
105 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
106 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
107 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
108 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
109 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
110 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
111 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
112 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
113 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
114 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
115 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | pending
116 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | pending
117 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | pending
118 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | pending
119 mock-up | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
120 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
121 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
122 | A | 1 |  | done | done | done | done |  | done |  | N/A |  | done
201 | A | 2 |  | done | no pipe | done | no pipe |  | pending |  | N/A |  | pending
202 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | pending
203 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
204 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | pending
205 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | no wire bed room
206 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | pending
207 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | pending
208 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
209 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
210 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
211 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
212 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
213 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
214 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
215 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
216 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
217 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
218 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
219 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
220 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
221 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | pending
222 | A | 2 |  | done | done | done | done |  | done |  | N/A |  | done
301 | A | 3 |  | pending | done | done | no pipe |  | pending |  | N/A |  | pending
302 | A | 3 |  | done | pending | done | no pipe |  | done |  | N/A |  | pending
303 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
304 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | no pipe
305 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
306 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
307 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | no pipe
308 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
309 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
310 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
311 | A | 3 |  | done | done | done | pending |  | done |  | N/A |  | done
312 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
313 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
314 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
315 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
316 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
317 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
318 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
319 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
320 | A | 3 |  | pending | done | done | No ONU |  | done |  | N/A |  | done
321 | A | 3 |  | done | done | done | done |  | done |  | N/A |  | done
322 | A | 3 |  | done | done | done | done |  | no pipe |  | N/A |  | done
401 | A | 4 |  | pending | no pipe | done | No ONU |  | pipe pending |  | N/A |  | pipe pending
402 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
403 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
404 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | pipe pending
405 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
406 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
407 | A | 4 |  | done | done | done | pending |  | pipe pending |  | N/A |  | pipe pending
408 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
409 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
410 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
411 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
412 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
413 | A | 4 |  | done | done | done | pending |  | done |  | N/A |  | done
414 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
415 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
416 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
417 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
418 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
419 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
420 | A | 4 |  | pending | done | done | No ONU |  | done |  | N/A |  | done
421 | A | 4 |  | done | done | done | done |  | pending civil work |  | N/A |  | done
422 | A | 4 |  | done | done | done | done |  | done |  | N/A |  | done
501 | A | 5 |  | done | no pipe | done | no ONU |  | done |  | N/A |  | no pipe
502 | A | 5 |  | done | done | done | no pipe |  | done |  | N/A |  | no pipe
503 | A | 5 |  | done | done | done | no pipe |  | no pipe |  | N/A |  | pending
504 | A | 5 |  | done | done | done | no pipe |  | pending |  | N/A |  | pending
505 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
506 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
507 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
508 | A | 5 |  | done | done | done | pending |  | done |  | N/A |  | done
509 | A | 5 |  | done | done | done | pending |  | done |  | N/A |  | done
510 | A | 5 |  | done | done | done | no pipe |  | done |  | N/A |  | done
511 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
512 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | no pipe
513 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
514 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
515 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
516 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
517 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
518 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
519 | A | 5 |  | done | done | done | done |  | done |  | N/A |  | done
520 | A | 5 |  | pending | done | done | no ONU |  | done |  | N/A |  | no pipe
521 | A | 5 |  | done | done | done | done |  | civil work pending |  | N/A |  | no pipe
522 | A | 5 |  | done | done | done | done |  | no pipe |  | N/A |  | done
601 | A | 6 |  | done | done | done | pending |  | pending |  | N/A |  | pending
602 | A | 6 |  | pending | done | done | pending |  | done |  | N/A |  | pending
603 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
604 | A | 6 |  | done | done | done | done |  | pending |  | N/A |  | pending
605 | A | 6 |  | done | done | done | pending |  | done |  | N/A |  | done
606 | A | 6 |  | done | done | done | pending |  | done |  | N/A |  | done
607 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | no pipe
608 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
609 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | pending
610 | A | 6 |  | done | done | done | pending |  | done |  | N/A |  | done
611 | A | 6 |  | done | done | done | pending |  | done |  | N/A |  | done
612 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
613 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
614 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
615 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | pending
616 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
617 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | pending
618 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | done
619 | A | 6 |  | done | done | done | done |  | done |  | N/A |  | pending
620 | A | 6 |  | pending | done | done | no ONU |  | no pipe |  | N/A |  | pending
621 | A | 6 |  | done | done | done | done |  | civil work pending |  | N/A |  | no pipe
622 | A | 6 |  | done | done | done | done |  | no pipe |  | N/A |  | done
701 | A | 7 |  | done | done | done |  |  |  |  | N/A
702 | A | 7 |  | done | done | done | done |  |  |  | N/A
703 | A | 7 |  | done | done | done |  |  |  |  | N/A |  | done
704 | A | 7 |  | done | done | done |  |  |  |  | N/A
705 | A | 7 |  | done | done | done |  |  |  |  | N/A |  | done
706 | A | 7 |  | done | done | done |  |  | done |  | N/A |  | done
707 | A | 7 |  | done | done | done | done |  | done |  | N/A
708 | A | 7 |  | done | done | done | done |  | done |  | N/A |  | done
709 | A | 7 |  | done | done | done |  |  | done |  | N/A
710 | A | 7 |  | done | done | done |  |  | done |  | N/A
711 | A | 7 |  | done | done | done | done |  | done |  | N/A
712 | A | 7 |  | done | done | done |  |  | done |  | N/A
713 | A | 7 |  | done | done | done |  |  | done |  | N/A
714 | A | 7 |  | done | done | done |  |  |  |  | N/A
715 | A | 7 |  | done | done | done |  |  |  |  | N/A
716 | A | 7 |  | done | done | done |  |  |  |  | N/A
717 | A | 7 |  | done | done | done |  |  |  |  | N/A
718 | A | 7 |  | done | done | done | done |  |  |  | N/A
719 | A | 7 |  | done | done | done | done |  |  |  | N/A
720 | A | 7 |  | pending | done | done | done |  |  |  | N/A
721 | A | 7 |  | done | done | done | done |  |  |  | N/A
722 | A | 7 |  | done | done | done | done |  |  |  | N/A
801 | A | 8
802 | A | 8
803 | A | 8
804 | A | 8
805 | A | 8
806 | A | 8
807 | A | 8
808 | A | 8
809 | A | 8
810 | A | 8
811 | A | 8
812 | A | 8
813 | A | 8
814 | A | 8
815 | A | 8
816 | A | 8
817 | A | 8
818 | A | 8
819 | A | 8
820 | A | 8
821 | A | 8
822 | A | 8
901 | A | 9 |  | done | done | done | pending |  | pending |  | N/A |  | pending
902 | A | 9 |  | pending | done | done | pending |  | done |  | N/A |  | pending
903 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
904 | A | 9 |  | done | done | done | done |  | pending |  | N/A |  | pending
905 | A | 9 |  | done | done | done | pending |  | done |  | N/A |  | done
906 | A | 9 |  | done | done | done | pending |  | done |  | N/A |  | done
907 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | no pipe
908 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
909 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | pending
910 | A | 9 |  | done | done | done | pending |  | done |  | N/A |  | done
911 | A | 9 |  | done | done | done | pending |  | done |  | N/A |  | done
912 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
913 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
914 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
915 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | pending
916 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
917 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | pending
918 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | done
919 | A | 9 |  | done | done | done | done |  | done |  | N/A |  | pending
920 | A | 9 |  | pending | done | done | no ONU |  | no pipe |  | N/A |  | pending
921 | A | 9 |  | done | done | done | done |  | civil work pending |  | N/A |  | no pipe
922 | A | 9 |  | done | done | done | done |  | no pipe |  | N/A |  | done

## Floors
TOWER | A | ELV Floors Work Prograsse
Last Updadte : | 25/06/2026
Time : | 12.3
ELV system | Point | Location | Additional details | Phase | [7 empty] | Floor | Completed works | Nots
|  |  |  | Preparation |  | Preliminary work |  | Implementation |  | Test
|  |  |  | Study of designs and specifications | Supply of materials and equipment | Pipeline drilling (Conduits) | Wiring | install devices | Configu Devices | System tuning | Cable testing
Bassment 1
CCTV | B1 CAM 1 | STAIR 2 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 1
| B1 CAM 2 | STAIR 1 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 2
| B1 CAM 3 | ENTRY-1 | 25% OBS VIEW | done |  | done | done |  |  |  |  | Bassment 3
| B1 CAM 4 | ENTRY-2 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 4
| B1 CAM 5 | LIFT LOBBY-1 | 25% OBS VIEW | done |  | done | done |  |  |  |  | Bassment 5
| B1 CAM 6 | LIFT LOBBY-2 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 6
| B1 CAM 7 | VIEW-1 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 7
| B1 CAM 8 | VIEW-2 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 8
| B1 CAM 9 | RAMP1 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 9
| B1 CAM 10 | DRIVE WAY1 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 10
| B1 CAM 11 | DRIVE WAY2 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 11
| B1 CAM 12 | DRIVE WAY3 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 12
| B1 CAM 13 | DRIVE WAY4 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 13
| B1 CAM 14 | DRIVE WAY5 | 120% ID VIEW | done |  | done | done |  |  |  |  | Bassment 14
| B1 CAM 15 | RAMP2 | 10% DET VIEW | done |  | done | done |  |  |  |  | Bassment 15
Access Control | CR: Card Reader | Lift lobby 1 | [9 empty] | Bassment 16
| ML: Magnetic Lock (القفل المغناطيسي) | Lift lobby 2 | [9 empty] | Bassment 17
| DRC: Door Release/Contact (جهاز إطلاق/اتصال الباب) | Lift lobby 3 | [9 empty] | Bassment 18
| DC: Door Contact (مستشعر حالة الباب) | Lift lobby 4 | [9 empty] | Bassment 19
| JB: Junction Box (صندوق التوصيل) | Lift lobby 5 | [9 empty] | Bassment 20
| DB: Distribution Board (لوحة التوزيع) | Lift lobby 6 | [9 empty] | Bassment 21
| LC: Lock Controller (متحكم القفل) | Lift lobby 7 | [9 empty] | Bassment 22 |  |  |  | Flat Num | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 213 | 214
| CR: Card Reader | Stiar-2 | [9 empty] | Bassment 23 |  |  |  | Fiber Optic | 214: N/A
| ML: Magnetic Lock (القفل المغناطيسي) | Stiar-3 | [9 empty] | Bassment 24
| DC: Door Contact (مستشعر حالة الباب) | Stiar-4 | [9 empty] | Bassment 25
| JB: Junction Box (صندوق التوصيل) | Stiar-5 | [9 empty] | Bassment 26
| DB: Distribution Board (لوحة التوزيع) | Stiar-6 | [9 empty] | Bassment 27 |  |  |  | Inter Come | pendding | pendding Long spring cable pulling required | pendding Long spring cable pulling required | done | done | pendding | done | done | done | done | done | done | N/A
Bassment 2
CCTV | [11 empty] | Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Access Control | [11 empty] | Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Bassment 2
Ground Floor
CCTV | [11 empty] | Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Access Control | [11 empty] | Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Gate Barrier | [11 empty] | Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
Ground Floor
poduim Floor
CCTV | [11 empty] | poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
Access Control | [11 empty] | poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
Gate Barrier | [11 empty] | poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
poduim Floor
1 St floor
CCTV | 1st flr CAM 1 | lift loby1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 2 | lift loby2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 3 | stair1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 4 | stair2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 5 | gym entry1 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 6 | gym entry2 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 7 | over view1 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 8 | over view2 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 9 | over view3 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 10 | over view4 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 11 | over view5 |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 12 | over view5 |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 13 | over view1, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 14 | over view2, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 15 | over view3, swimming pool area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 16 | over view1, gardening area |  | done |  | done | done |  |  |  |  | 1
| 1st flr CAM 17 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 18 | over view2, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
| 1st flr CAM 19 | over view4, gardening area |  | done |  | pendding | pendding |  |  |  |  | 1
intercom | 101 |  |  | done |  | done | [5 empty] | 1
| 102 |  |  | done |  | done | pendding |  |  |  |  | 1
| 103 |  |  | done |  | done | pendding |  |  |  |  | 1
| 104 |  |  | done |  | done | [5 empty] | 1
| 105 |  |  | done |  | done | [5 empty] | 1
| 106 |  |  | done |  | pendding | pendding |  |  |  |  | 1
| 107 |  |  | done |  | done | [5 empty] | 1
| 108 |  |  | done |  | done | [5 empty] | 1
| 109 |  |  | done |  | done | [5 empty] | 1
| 110 |  |  | done |  | done | [5 empty] | 1
| 111 |  |  | done |  | done | [5 empty] | 1
| 112 |  |  | done |  | done | [5 empty] | 1
| 113 |  |  | done |  | done | [5 empty] | 1
Fiber Optic | 101 | [10 empty] | 1
| 102 | [10 empty] | 1
| 103 | [10 empty] | 1
| 104 | [10 empty] | 1
| 105 | [10 empty] | 1
| 106 | [10 empty] | 1
| 107 | [10 empty] | 1
| 108 | [10 empty] | 1
| 109 | [10 empty] | 1
| 110 | [10 empty] | 1
| 111 | [10 empty] | 1
| 112 | [10 empty] | 1
| 113 | [10 empty] | 1
2nd Floor
CCTV | 2nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2 |  |  | pendding Long spring cable pulling required
| 2nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 2 |  |  | pendding Long spring cable pulling required
| 2nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
| 2nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 2
intercom | 201 |  |  | done |  | done | [5 empty] | 2
| 202 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 203 |  |  | done |  | pendding | pendding |  |  |  |  | 2
| 204 |  |  | done |  | done | done |  |  |  |  | 2
| 205 |  |  | done |  | done | done |  |  |  |  | 2
| 206 |  |  | done |  | done | done |  |  |  |  | 2
| 207 |  |  | done |  | done | done |  |  |  |  | 2
| 208 |  |  | done |  | done | done |  |  |  |  | 2
| 209 |  |  | done |  | done | done |  |  |  |  | 2
| 210 |  |  | done |  | done | done |  |  |  |  | 2
| 211 |  |  | done |  | done | done |  |  |  |  | 2
| 212 |  |  | done |  | done | done |  |  |  |  | 2
| 213 |  |  | done |  | done | done |  |  |  |  | 2
| 214 |  |  | done |  | done | done |  |  |  |  | 2
Fiber Optic | 201 |  |  | done | [7 empty] | 2
| 202 |  |  | done | [7 empty] | 2
| 203 |  |  | done | [7 empty] | 2
| 204 |  |  | done | [7 empty] | 2
| 205 |  |  | done | [7 empty] | 2
| 206 |  |  | done | [7 empty] | 2
| 207 |  |  | done | [7 empty] | 2
| 208 |  |  | done | [7 empty] | 2
| 209 |  |  | done | [7 empty] | 2
| 210 |  |  | done | [7 empty] | 2
| 211 |  |  | done | [7 empty] | 2
| 212 |  |  | done | [7 empty] | 2
| 213 |  |  | done | [7 empty] | 2
| 214 |  |  | done | [7 empty] | 2
3nd Floor
CCTV | 3nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 3
| 3nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
| 3nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 3
intercom | 301 |  |  | done |  | done | [5 empty] | 3
| 302 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 303 |  |  | done |  | pendding | pendding |  |  |  |  | 3
| 304 |  |  | done |  | done | done |  |  |  |  | 3
| 305 |  |  | done |  | done | done |  |  |  |  | 3
| 306 |  |  | done |  | done | done |  |  |  |  | 3
| 307 |  |  | done |  | done | done |  |  |  |  | 3
| 308 |  |  | done |  | done | done |  |  |  |  | 3
| 309 |  |  | done |  | done | done |  |  |  |  | 3
| 310 |  |  | done |  | done | done |  |  |  |  | 3
| 311 |  |  | done |  | done | done |  |  |  |  | 3
| 312 |  |  | done |  | done | done |  |  |  |  | 3
| 313 |  |  | done |  | done | done |  |  |  |  | 3
| 314 |  |  | done |  | done | done |  |  |  |  | 3
Fiber Optic | 301 |  |  | done | [7 empty] | 3
| 302 |  |  | done | [7 empty] | 3
| 303 |  |  | done | [7 empty] | 3
| 304 |  |  | done | [7 empty] | 3
| 305 |  |  | done | [7 empty] | 3
| 306 |  |  | done | [7 empty] | 3
| 307 |  |  | done | [7 empty] | 3
| 308 |  |  | done | [7 empty] | 3
| 309 |  |  | done | [7 empty] | 3
| 310 |  |  | done | [7 empty] | 3
| 311 |  |  | done | [7 empty] | 3
| 312 |  |  | done | [7 empty] | 3
| 313 |  |  | done | [7 empty] | 3
| 314 |  |  | done | [7 empty] | 3
4th Floor
CCTV | 4nd flr CAM 1 | lift loby1 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 2 | lift loby2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 3 | stair1 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 4 | stair2 | 10% DETECTION VIEW | done |  | pendding | done |  |  |  |  | 4
| 4nd flr CAM 5 | cr view1 | 25% OBSERVATION VIEW | done |  | done | pending |  |  |  |  | 4 |  | long spring needed
| 4nd flr CAM 6 | cr view2 | 25% OBSERVATION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 7 | cr view3 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
| 4nd flr CAM 8 | cr view4 | 10% DETECTION VIEW | done |  | done | done |  |  |  |  | 4
4
Inter Come | 401 |  |  | done | done | done | done |  |  |  |  | 4
| 402 | [5 empty] | done |  |  |  |  | 4
| 403 | [5 empty] | pending |  |  |  |  | 4
| 404 | done |  |  |  |  | pending |  |  |  |  | 4
| 405 | done |  | done |  | done | done |  |  |  |  | 4
| 406 | done |  | done |  | done | done |  |  |  |  | 4
| 407 | done |  | done |  | done | done |  |  |  |  | 4
| 408 | done |  | done |  | done | done |  |  |  |  | 4
| 409 | done |  | done |  | done | done |  |  |  |  | 4
| 410 | done |  | done |  | done | done |  |  |  |  | 4
| 411 | done |  | done |  | done | done |  |  |  |  | 4
| 412 | done |  | done |  | done | done |  |  |  |  | 4
| 413 | done |  | done |  | done | done |  |  |  |  | 4
| 414 | done |  | done |  | done | done |  |  |  |  | 4
| 415 | done |  | done |  | done | done |  |  |  |  | 4